## Test Plan
Test Plan
Project Name | Zoho Books Mobile Application Testing
Document Version | 1
Date | 24/06/2025
Prepared By | Sharif Jobayed
Purpose: | This document outlines the test plan for functional and device compatibility testing of the Zoho Books mobile application. The objective is to ensure the app's key features work as expected across various devices and operating systems, and to identify any functional or UI/UX issues.
Objective: | To evaluate the functional correctness and device compatibility of the Zoho Books mobile application.
Scope: | Functional Testing: Key features including user registration/login, invoice management, customer/product addition, financial reports, payment gateways, notifications, access control, and logout.
Device Compatibility Testing: Testing across at least 3 Android devices with different specs, 3 Android OS versions, and 1 iOS emulator, including screen orientation changes.
Test Environment | Android Devices: At least 3 different Android devices with varying specifications (low-end, mid-range, high-end).
Android OS Versions: At least 3 different Android versions (e.g., Android 10, Android 12).
iOS Devices/Emulators: At least 1 iOS device or emulator (e.g., iOS emulator on Windows).
Network Conditions: Stable Wi-Fi/Mobile Data connection.
App Version: Zoho Books Mobile Application (latest version from Google Play Store)."
Entry Criteria | 1. The Zoho Books mobile application is available for download on specified devices/emulators.
2. A free trial account can be successfully created.
3. All necessary test data and configurations are prepared."
Exit Criteria | 1. All high-priority test cases have been executed.
2. All critical and high-severity bugs have been reported and verified (if retesting is possible).
3. All planned functional and compatibility tests have been completed. "
Compatibility testing using emulators (and real devices if available) to simulate diverse environments.
Deliverables | 1. Test Plan Sheet
2. Test Scenarios Sheet
3. Test Suites Sheet
4. User Authentication Test Cases Sheet
5. Invoice Management Test Cases Sheet
6. Customer & Product Management Test Cases Sheet
7. Financial Reports Test Cases Sheet
8. Payment Gateway & Notifications Test Cases Sheet
9. Device Compatibility Report Sheet
10. Bug Report Sheet
11. Test Summary Report Sheet
12. Test Metrics Sheet
Tested by: | Sharif Jobayed
All deliverables to be submitted in a structured report format (Excel or Word or PDF) within 1 day

## Test Scenarios
Test Scenarios
Scenario ID | Type | Description | Priority | Test Cases Count | Remarks
TS001 | Functional | User can register and log in successfully | High | 10
TS002 | Functional | User can create, edit, and delete invoices | High | 7
TS003 | Functional | User can add customers and products/services | High | 3
TS004 | Functional | User can view financial reports | Medium | 3
TS005 | Functional | User can integrate with payment gateways | High | 2
TS006 | Functional | User receives notifications for due invoices | High | 2
TS007 | Functional | Access control works based on user roles | High | 1 | Can not add more users using disposable emails/invitaions
TS008 | Functional | User can log out successfully | Medium | 1
TS009 | Device Compatibility | App UI renders correctly on different screen sizes | High |  | Can not be done due to devise shortage
TS010 | Device Compatibility | App functions properly on various Android versions | High |  | Can not be done due to devise shortage
TS011 | Device Compatibility | App handles screen orientation changes | Medium | 2

## Test Suites
Test Suites
Suite ID | Suite Name | Description
SUITE01 | User Authentication | Tests for registration, login, and logout
SUITE02 | Invoice Management | Tests for creating, editing, deleting invoices
SUITE03 | Customers and Products | Tests for adding customers and products
SUITE04 | Financial Reports | Tests for viewing financial reports
SUITE05 | Payment Gateways | Tests for payment gateway integration
SUITE06 | Notifications | Tests for notification functionality
SUITE07 | Access Control | Tests for role-based access
SUITE08 | Logout Functionality | Tests for logout process

## User Authentication Test Cases
Test Cases - User Authentication
ID | Scenario ID | Module | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS001 | User Authentication | Verify registration with valid email and password | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Open app 2. Click "Sign Up" 3. Browser opens 4. Enter Business Location 5. Enter Full Name 6. Enter Email Address 7. Enter Password 8. Tap "Create Account" | User registered and redirected to profile details screen | User registered successfully | Pass
TC002 | TS001 | User Authentication | Verify registration with disposable email and password | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "zt@yopmail.com" Password: "Hello1@Zoho" | 1. Open app 2. Click "Sign Up" 3. Browser opens 4. Enter Business Location 5. Enter Full Name 6. Enter Email Address 7. Enter Password 8. Tap "Create Account" | Displays Error "We are unable to create your account right now. Please contact support-as@zohocorp.com" | Error shown, registration fails | Pass
TC003 | TS001 | User Authentication | Verify registration with existing email | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" (Existing email) Password: "Hello1@Zoho" | 1. Open app 2. Click "Sign Up" 3. Browser opens 4. Enter Business Location 5. Enter Full Name 6. Enter Email Address 7. Enter Password 8. Tap "Create Account" | Displays Error "An account already exists for this email address. Sign in or use a different email address to sign up" | Error shown, registration fails | Pass
TC004 | TS001 | User Authentication | Verify login with correct credentials | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in User is already registered & verified email | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Open app 2. Click "Sign In" 3. Browser opens 4. Enter Email Address 5. Press "Next" 6. Enter Password 7. Tap "Sign In" | Login successful & lands on dashboard screen | User successfully logs in to the dashboard screen | Pass
TC005 | TS001 | User Authentication | Verify login with incorrect password | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in User is already registered & verified email | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello10@Zoho" | 1. Open app 2. Click "Sign In" 3. Browser opens 4. Enter Email Address 5. Press "Next" 6. Enter Password 7. Tap "Sign In" | Displays Error "Incorrect password. Please try again." & login fails | Error shown, registration fails | Pass
TC006 | TS008 | Logout | Verify logout functionality | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in User is already logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on the menu at the top-left 2. Tap "Settings" 3. Tap the power icon at the top-right 4. Tap log out | User successfully logs out to the login page | Log out successful | Pass
TC007 | TS001 | User Authentication | Verify registration with a weak password | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "test@xyz.com" Password: "weak" | 1. Open app 2. Click "Sign Up" 3. Browser opens 4. Enter Business Location 5. Enter Full Name 6. Enter Email Address 7. Enter Password 8. Tap "Create Account" | Displays Error "Password cannot be less than 8 characters" & registration fails | User registration fails | Pass | Potential issue: Weak password accepted
TC008 | TS001 | User Authentication | Verify registration with an invalid email format | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "invalid_email" Password: "Hello1@Zoho" | 1. Open app 2. Click "Sign Up" 3. Browser opens 4. Enter Business Location 5. Enter Full Name 6. Enter Email Address 7. Enter Password 8. Tap "Create Account" | Displays Error "Please enter a valid email address" & registration fails | User registration fails | Pass | Potential issue: Invalid email accepted
TC009 | TS001 | User Authentication | Verify login with an unregistered email | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "unregistered@xyz.com" Password: "Hello1@Zoho" | 1. Open app 2. Click "Sign In" 3. Browser opens 4. Enter Email Address 5. Press "Next" | Displays Error "This account cannot be found. Please use a different account or sign up for a new account." & the password field doesn't appear | Error displayed, no password field available & user login fails | Pass | Potential issue: Invalid email accepted
TC010 | TS001 | User Authentication | Verify password reset functionality | Device: Pixel 6a API 31 Android Version: 12 App installed, not logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Old Password: "Hello1@Zoho" New Password: "Hello2@Zoho" | 1. Open app 2. Tap Sign In 3. Browser opens 4. Enter registered Email Address 5. Tap Next 6. Tap "Forgot Password?" link 7. Verify CAPTCHA if there's any 8. Tap "Continue to reset password" 9. Enter the one-time password sent to the email 10. Enter the OTP 11. Tap verify 12. Enter the new password 13. Confirm the new password 14. Tap "Change Password" | User should be able to login using the new password | User successfully logs in to the dashboard screen | Pass
TC011 | TS001 | User Authentication | User registers via invitation link | - Device: Pixel 6a API 31 - Android Version: 12 - App installed, not logged in - User is already invited to sign up | - Business Location: Bangladesh - Full Name: "Max Payne" - Email Address: "mpayne@yopmail.com" - Password: "abcdEf@12345" | 1. The user taps on the invitation link in the mail 2. Tap Sign up 3. Browser opens 4. Enter Email Address 5. Enter Password 6. Tap "Create Account" | User registered and redirected to profile details screen | Error `Unable to create account` pops up | Fail

## Invoice Management Test Cases
Test Cases - Invoice Management
ID | Scenario ID | Module | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS002 | Invoice Management | Verify creation of invoice with valid details | User is logged in to the dashboard | Customer: John Doe Product is already created Item: Headphone | 1. Navigate to "New Invoice" 2. Enter customer 3. Enter Order Number & other fields with valid data 4. Tap "Add Line Item" 5. Choose "Headphone" for the Item field 6. Tap "Save" button 7. Tap "Save as Draft" at the top-right | Invoice created successfully | Invoice created | Pass
TC002 | TS002 | Invoice Management | Verify creation without mandatory fields | User is logged in to the dashboard | N/A | 1. Navigate to "New Invoice" 2. Leave customer field blank 3. Tap "Save as Draft" at the top-right | "Select a Customer from the dropdown" tooltip is displayed & the invoice isn't saved | Tooltip displayed, Invoice not created | Pass
TC003 | TS002 | Invoice Management | Verify editing an existing invoice | Invoice exists | Update the order number | 1. Tap the menu icon at the top-left 2. Expand the "Sales" submenu 3. Tap "Invoices" 4. Tap "All" tab 5. Tap on a draft 6. Tap the edit icon at the top 7. Edit the order number something else 8. Tap "Save as Draft" at the top-right | Invoice updated successfully & the new order number is displayed on the invoice | Update successful | Pass
TC004 | TS002 | Invoice Management | Verify deletion of an invoice | Invoice exists | N/A | 1. Tap the menu icon at the top-left 2. Expand the "Sales" submenu 3. Tap "Invoices" 4. Tap "All" tab 5. Tap on a draft 6. Tap the 3-dots menu at the top-right of the invoice 7. Tap "Delete" 8. Tap "Delete" for the delete confirmation pop-up | Deletion success notification is displayed & the invoice deleted successfully | Deletion successful | Pass
TC011 | TS002 | Invoice Management | Verify the user can send new invoices | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - Customer exists | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on New Invoice 2. Tap on Customer Name 3. Type first 2 letters of a customer’s name 4. Select a customer 5. Check all required fields are filled up 6. Scroll down & tap on “Add Line Item” button 7. Select an item in the Item field 8. Tap on Save 9. On the “New Invoice” screen, tap on the 3 dots at the top right 10. Tap on Save and Send 11. On the Email screen, check if the invoice is attached 12. At the top right of the screen, tap on the Send icon | The invoice should be sent & user on the sent invoice screen | The invoice was sent & user was on the sent invoice screen | Pass
TC012 | TS002 | Invoice Management | Verify the user can’t send new invoices without a line item | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - Customer exists | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on New Invoice 2. Tap on Customer Name 3. Type first 2 letters of a customer’s name 4. Select a customer 5. Check all required fields are filled up 6. On the “New Invoice” screen, tap on the 3 dots at the top right 7. Tap on Save and Send | An alert saying “You need to add at least one line item” pops up & invoice sending fails | Alert popped up & invoice sending failed | Pass
TC013 | TS002 | Invoice Management | Verify the user can send new invoices | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - Customer exists | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on New Invoice 2. Tap on Customer Name 3. Type first 2 letters of a customer’s name 4. Select a customer 5. Check all required fields are filled up 6. Scroll down & tap on “Add Line Item” button 7. Select an item in the Item field 8. Tap on Save 9. On the “New Invoice” screen, tap on the 3 dots at the top right 10. Tap on Save and Send 11. On the Email screen, check if the invoice is attached 12. At the top right of the screen, tap on the Send icon | The invoice should be sent & user on the sent invoice screen | The invoice was sent & user was on the sent invoice screen | Pass

## Customers and Products Test Cas
Test Cases – Customer & Products
ID | Scenario ID | Module | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS003 | Items | Verify creation of item with valid data | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - User is on the dashboard screen | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" - Item Name: "Test Item" - Selling Price: 3000 - Cost Price: 2000 - Account: "Sales" | 1. Tap on the 3 dash menu on the top left 2. Tap `Items` 3. Tap `+` icon on the bottom right 4. On the `New Item` screen, tap on the `Goods` checkbox 5. Type the name in the `Item Name` field 6. Under the `Sales Information`, type the price `3000` in the `Selling Price` field 7. Under the `Purchase Information` type `2000` in the `Cost Price` field 8. Select an account from the `Account` dropdown 9. Tap `Save` on the top right of the screen | The item should be added to the Items list | The item was added to the items list | Pass
TC002 | TS003 | Items | Verify item creation fails when Selling Price is non-numeric | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - User is on the dashboard screen | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" - Item Name: "Test Item" - Selling Price: "Three Thousand" (invalid) - Cost Price: 2000 - Account: "Sales" | 1. Navigate to New Item screen 2. Fill all valid fields except Selling Price 3. Enter "Three Thousand" in Selling Price 4. Tap Save | - App should show validation error - Item should not be added. | Validation error displayed & the item isn’t added to the list | Pass
TC003 | TS003 | Items | Missing Item Name | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - User is on the dashboard screen | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" - Item Name: "Test Item" - Selling Price: 3000 - Cost Price: 2000 - Account: "Sales" | 1. Tap on the 3 dash menu 2. Tap Items 3. Tap + icon 4. Tap Goods checkbox 5. Leave Item Name blank 6. Enter 3000 in Selling Price 7. Enter 2000 in Cost Price 8. Select an account 9. Tap Save | - An error message like "Item Name is required" should appear. - Item should not be saved. | Error displayed & the item wasn’t added | Pass

## Financial Reports Test Cases
Test Cases – Financial Reports
ID | Scenario ID | Module | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS004 | Report | Verify Accrual based report visibility | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - User is on the dashboard screen | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on the 3 dash menu on the top left 2. Tap `Reports` 3. Tap `Balance Sheet` 4. Select current/past date in the `Date` field 5. Select `Accrual` in the `Report Basis` field 6. Tap `Run Report` | Balance Sheet till the selected date should be displayed | Balance Sheet till the selected date is displayed | Pass
TC002 | TS004 | Report | Verify Sales by customer report is displayed | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - User is on the dashboard screen | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on the 3 dash menu on the top left 2. Tap `Reports` 3. Tap `Sales by Customer` 4. Select date range for `This Week` | Sales by Customer report should be displayed for this week | Sales by Customer report is displayed for this week | Pass
TC003 | TS004 | Report | Verify report isn’t displayed if there’s no connection | - Device: Symphony Z55 - Android Version: 12 - App installed, and logged in - User is on the dashboard screen | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on the 3 dash menu on the top left 2. Tap `Reports` 3. Tap `Sales by Customer` 4. Select date range for `This Week` 5. Turn off the network | Error `Problem in connection. Please try again` should pop up & the report should not display | Error popped up & no report displayed | Pass

## Payment Gateways Test Cases
Test Cases – Payment Gateways
ID | Scenario ID | Module | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TS001 | TS005 | Banking | Add a bank | - App installed - User logged in & on the Dashboard screen | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" | 1. Tap on the 3 dash menu on the top left 2. Tap `Banking` 3. On the `Banking Overview` screen, tap `+` button 4. Select `Bank` 5. Fill all the required fileds 6. Tap `Save` button | The bank should be added under the `Active Accounts` | Bank added | Pass
TS002 | TS005 | Banking | Add a Credit Card with existing name | - App installed - User logged in & on the Dashboard screen | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" | 1. Tap on the 3 dash menu on the top left 2. Tap `Banking` 3. On the `Banking Overview` screen, tap `+` button 4. Select `Credit Card` 5. Type a name that already exists as a Bank Account 5. Fill all the required fileds 6. Tap `Save` button | Error `Existing Account Name` should be displayed & the credit card account should not be added | Error displayed & the account is not added | Pass

## Notifications Test Cases
Test Cases – Payment Gateway
ID | Scenario ID | Module / Screen | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS006 | Dashboard | Overdue invoice count displayed on Dashboard | Device: Symphony Z55 Android Version: 12 App installed, user logged in to the Dashboard | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" | 1. Check if the `Overdue Invoices` with count is displayed 2. Tap on it | The list of overdue invoices should be displayed | The list of overdue invoices are displayed | Pass
TC002 | TS006 | Dashboard | Overdue invoice count displayed in Notifications | - Device: Symphony Z55 - Android Version: 12 - App installed, user logged in to the Dashboard | - Business Location: Bangladesh - Full Name: "Sharif Jobayed" - Email Address: "sj@xyz.com" - Password: "Hello1@Zoho" - There are overdue invoices in the invoices list | 1. Check for new notifications 2. Tap on the notification bell icon | - The overdue invoices notification should be displayed - A push notification should be received as well | - The overdue invoices notification isn’t displayed - No push notification received | Fail

## Access Control Test Cases
Test Cases – Access Control
ID | Scenario ID | Module | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS007 | Users | Invite an user | App is installed & the user is logged in to the Dashboard | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Password: "Hello1@Zoho" | 1. Tap on the 3 dash menu on the top left 2. Tap `Settings > Users` 3. On the Users screen, tap on the `+` icon 4. Enter name `Max Payne` 5. Enter email `mpayne@yopmail.com` 6. Tap `Send` at the top right | The invited user should be listed on the Users list | The invited user is listed on the Users list | Pass

## Device Compatibility Test Cases
Test Cases – Device Compatibility
ID | Scenario ID | Module / Screen | Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | TS011 | Dashboard Screen | Dashboard items don’t break upon rotating the screen | - Device: Symphony Z55 - Android Version: 12 - Phone is in landscape mode - App installed, and logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Old Password: "Hello1@Zoho" New Password: "Hello2@Zoho" | 1. Observe the dashboard items, layout, and overall UI to ensure no elements are broken, overlapping, truncated, or misplaced. 2. Rotate the device back from Landscape to Portrait mode. 3. Observe the dashboard items, layout, and overall UI again to ensure elements adjust correctly and no breaking occurs. | Items should be aligned to the expected design | Items are aligned to the expected design | Pass
TC002 | TS011 | Dashboard Screen | Verify dashboard items alignment and responsiveness after multiple rapid rotations | - Device: Symphony Z55 - Android Version: 12 - Phone is in landscape mode - App installed, and logged in | Business Location: Bangladesh Full Name: "Sharif Jobayed" Email Address: "sj@xyz.com" Old Password: "Hello1@Zoho" New Password: "Hello2@Zoho" | 1. Open Zoho Books app, log in, and navigate to the Dashboard screen. 2. Rapidly rotate the device between Portrait and Landscape modes 5-10 times. 3. Stop rotation and observe the Dashboard UI. | Dashboard items should consistently adapt to each orientation without breaking, overlapping, or misaligning. UI elements should render smoothly and be fully visible. | Items adapt screen rotations without breaking the UI | Pass

## Device Compatibility Report
Device Compatibility Test Report
Device Brand | Model | OS Version | Screen Size | Orientation | Issues Count
Samsung | Galaxy A12 | Android 10 | 6.5" | Portrait | Not Tested
Google | Pixel 6.a | Android 12 | 6.17" | Portrait | None
Google | Pixel 6.a | Android 12 | 6.52" | Portrait | None
Apple | iPhone 12 (emulator) | iOS 14 | 6.1" | Portrait | Not Tested

## Bug Reports
Bug Reports
Bug ID | Module | Description | Preconditions | Steps to Reproduce | Expected Behavior | Actual Behavior | Severity | Priority | Device | OS Version | Image / Screen cast
Bug001 | Notifications | No notifications for overdue invoices | - App installed - User is logged in | 1. Check for new notifications 2. Tap on the notification bell icon | - The overdue invoices notification should be displayed - A push notification should be received as well | - The overdue invoices notification isn’t displayed - No push notification received | Low | Medium | Symphony | Z55
Bug002 | User Registration | User can not sign up via invitation link | - App installed - User is invited but not logged in - User is in their mailbox | 1. The user taps on the invitation link in the mail 2. Tap Sign up 3. Browser opens 4. Enter Email Address 5. Enter Password 6. Tap "Create Account" | User registered and redirected to profile details screen | Error `Unable to create account` pops up | High | High | Google Pixel | 6a API 31

## Test Report
Test Report | [5 empty] | Result :
Project Name | Zoho Books Mobile Application Testing |  |  |  |  | Total No. | Status
Written By | Sharif Jobayed
Executed By | Sharif Jobayed |  |  |  |  | 26 | PASS
Reviewed By | Sharif Jobayed |  |  |  |  | 2 | FAIL
TEST EXECUTION REPORT | [5 empty] | 0 | Not Executed
[6 empty] | 0 | Out of Scope
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
31 | 26 | 2 | 0 | 0 | 28
Grand Total | 26 | 2 | 0 | 0 | 28
LIMITATIONS
Documents |  |  | Received | Useful
FRS |  |  | No | Yes
USER STORY |  |  | No | Yes